## ECW Annual Workplan 2020
ECW Annual Work Plan 2020
Strategic Objective | Indicator name | Ref. in ECW results framework | Baseline or current status (if applicable) |  | Target 2020 |  |  | Comments
ECW Strategic Objective 1: Increase Political Support to Education in Crises Increase high-level attention with an aim towards greater equity of response, with an emphasis on the most vulnerable and reaching neglected crises. | Total annual funding to education in emergencies as a % of global humanitarian funding. | S1.1 | 4.3% of sector specific funding |  | 5.0% of sector-specific funding
| Percentage of crisis-affected countries where humanitarian country-based pooled funds allocate at least 10% to education | S1.3 | 18% |  | 20%
| Proportion of Humanitarian appeals that include an Education component | S1.4 | 83% |  | 90%
| Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
High-level Result I : Commitments to the “New Way of Working” in EiE through humanitarian-development coherence are strengthened and applied through the ECW model.
| Results 1.1: ECW systemic outcomes in support of EiE are advanced through Advocacy and Communications initiatives | 1.1.1 | Establish a media partnership to widely promote ECW's results, and advocate for the ECW model, including supporting the ECW Director to optimize her outreach as advocate for prioritizing education in crisis through the New Way of Working towards humanitarian-development coherence. |  |  | X | X | X | X | Communications and Advocacy with the selected international media outlet
|  | 1.1.2 | Expand and promote ECW communication products and digital contents providing visibility to ECW's work across the humanitarian-development spectrum, and throughout the COVID Pandemic.Products and messages will be aligned with COVID19 response priorities as deemed relevant. |  |  | X | X | X | X | Communications and Advocacy with implementing partners
|  | 1.1.3 | Secure ECW's participation and visibility in advocacy platforms and policy dialogue fora on the UN Reform, the New Way of Working, the humanitarian-development nexus and the CRRF,and COVID19 platforms during emergency and recovery (e.g.GEC). |  |  | X | X | X | X | ECW Secretariat with HLSG/EXCOM and partners
| Result 1.2: Broad visibility of ECW's values of collaboration and partnerships is ensured | 1.2.1 | Finalize and disseminate ECW visibility and communications guidance for grantees |  |  | X | X |  |  | Communications and Advocacy with Country Leads
|  | 1.2.2 | Develop and launch a revamped website (to better meet ECW’s stakeholders’ information needs, feature ECW’s rapidly evolving operations and results). |  |  | X | X | X |  | Communications and Advocacy
|  | 1.2.3 | Support and ensure multi-stakeholders joint communication on ECW investments (including launch events and campaigns) |  |  | X | X | X | X | Communications and Advocacy with ECW Secretariat and partners
High-level Result II: Policies are adopted to promote and ensure inclusive, safe and equitable quality education responses in EiE
| Result 2.1: Public awareness of education in emergencies and protracted crises is increased | 2.1.1 | Produce and distribute communication/advocacy content demonstrating the value of EiE, including a focus on content related to COVID resonse and advocacy, inclusion of refugees in educational programs at the national level, particularly at the secondary and tertiary levels |  |  | X | X | X | X | Communications and Advocacy with implementing partners and external vendors
|  | 2.1.2 | Increase ECW media engagement and coverage, including for ECW field visits |  |  | X | X | X | X | Communications and Advocacy and partners
|  | 2.1.3 | Elevate the voice of ECW beneficiaries, including refugee children and youth benefitting from quality inclusive education at the primary and secondary level |  |  | X | X | X | X | Communications and Advocacy
|  | 2.1.4 | Position ECW's voice in high-level global education policy fora and the ECW Director as a thought leader in the EiE sector, with a focus on gender, forced displacement and protection issues. |  |  | X | X | X | X | Communications and Advocacy
|  | 2.1.5 | Produce and/or support the development of policy briefing documentation on EIE |  |  | X | X | X | X | ECW Director with Country leads
High Level Result III: Political stakeholders adopt policies to increase finance to EiE, including through ECW
| Result 3.1 Engagement with CSOs to advocate for EiE further strengthened. | 3.1.1 | Continue to engage with CSOs networks to build on the 2019 global #act4Ed campaign to secure funding commitments for ECW in priority donor markets |  |  | X | X | X | X | Communications and Advocacy/Partnership & Donor Relations
| Result 3.2 ECW brand strengthened though the engagement of existing champions and new champions and celebrities | 3.2.1 | Extend ECW's engagement with high-level champions and celebrities to advocate for political commitments to EiE through ECW at the global, regional and national levels |  |  | X | X | X | X | Communications and Advocacy
|  | 3.2.2 | Strengthen ECW's engagement with Resident Coordinators/Humanitarian Coordinators coordinating humanitarian/development response in emergencies and protracted crisis countries. |  |  | X | X | X | X | Country leads
Strategic Objective | Indicator name | Ref. in ECW results framework | Baseline or current status (if applicable) | Target for 2020 -2021 |  |  |  | Comments
ECW Strategic Objective 2: Increase Financing For Education in Crises Raise significant additional resources to support interventions that improve access, quality, continuity, protection, equity and gender equality. | Total funding raised and leveraged by ECW at country and global level, disaggregated by budget type (humanitarian/other) | S2.1 | 560 M (global level) TBD (in-country) | 350M (global fund) 1.2 billion (in-country)
| Proportion of funding raised and leveraged as a result of: i) innovative financing; ii) non-traditional and private sources | S2.2 | TBD | TBD
| Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
High-level Result I: Resources are mobilized to bridge the remaining finance gap of 350 Million for the Global fund by at least 50% and the gap at In-country level by at least 30%.
| Result 1.1: Existing relations with donors is deepened to increase existing contributions by at least 20% | 1.1.1 | Reach out to ECW donors whose contributions have already been disbursed, to increase funding for the overall ECW RM target as well as for the emergency FER COVID19 response. |  |  | X | X | X | X | Partnership & Donor Relations with HLSG, ExCom and Civil Society Partners
|  | 1.1.2 | Reach out to annual and one time funding donors to pledge multi-year commitments to EiE and COVID response through ECW. |  |  | X | X | X | X | Partnership & Donor Relations with HLSG, ExCom and Civil Society Partners
|  | 1.1.3 | Produce Business Case on the value added for ECW's investments in supporting gender equality and empowerment of girls and women | [5 empty] | X | Gender Programme Manager/Communications and Advocacy
| Result 1.2: New partnerships with additional donors are established | 1.2.1 | Increase the share of emergent donors into ECW by at least 5% |  |  | X | X | X | X | Partnership & Donor Relations with Islamic development Bank and Dubai Cares and Education Above All
|  | 1.2.2 | Organize pledging moments for ECW in different regions including the Gulf States |  |  | X | X | X | X | Partnership & Donor Relations
|  | 1.2.3 | Increase ECW donor base by targeting countries that support education, though not current ECW donors, through strategic country visits to meet ministers, Parliamentarians and civil society |  |  | X | X | X | X | Partnership & Donor Relations Civil Society and missions to the UN
| Result 1.3: New Private sector donors are brought onboard | 1.3.1 | Increase the share of private sector contribution to ECW by at least 17%, ensure focus on COVID needs |  |  | X | X | X | X | Partnership & Donor Relations Global Citizen and others
|  | 1.3.2 | Promote new approaches and develop tools to enhance the integration of private sector donors into ECW programmes, COVID19 presents opportunities to promote innovation and new solutions that are conducive to public private partnership. |  |  |  | X |  |  | Partnership& Donor Relations
High-level result II : The Capacity of in-country partners to participate actively in bridging the finance gap for EiE (using FERs and MYRPS) is significantly improved to leverage at least an additional 1.2 billion USD.
| Result 2.1: The amount of resources mobilized in-country reach at least 500 Million USD in 2020 | 2.1.1 | Increase the number of MYRPs with in-country resource mobilization capacity (ensure an active Steering Committee in RM, RM specialist, RM and Advocacy action plan, and a Country Case for Investment in EiE&PC) |  |  | X | X | X | X | Country leads with Partnership & Donor Relations /Country Leads
|  | 2.1.2 | Support in-country partners to effectively participate and promote EiE&PC in-country and regional pledging events as well as other resource mobilization and advocacy opportunities |  |  |  | X | X | X | Country leads
|  | 2.1.3 | Develop the ECW technical support and guidelines for strengthening resource mobilization with FER and MYRP investments during all phases of implementation |  |  |  |  | X |  | Partnership & Donor Relations
|  | 2.1.4 | Operationalize SoPs for tracking of resource mobilization: - Finalize a tool to track resource mobilization under each MYRP - Pilot tracking systems in at least 3 MYRP countries - Finalize a tool to track more precisely the financial resources mobilized globally for EiE |  |  | X | X |  |  | M&E, Education Quality, Country leads, Grants Management/Finance
[7 empty] | X | X | X | M&E, Education Quality, Country leads, Grants Management
[7 empty] | X | X | X | M&E, Education Quality, Country leads, Grants Management
Strategic Objective | Indicator name | Ref. in ECW results framework | Baseline or current status (if applicable) | Target for 2020 |  |  |  | Comments
ECW Strategic Objective 3 : Improve Joint Planning and Responses Unite humanitarian and development efforts in support of national preparedness and responses to education crises through facilitating the development of joint programmes | Percentage of first emergency response countries where funds were disbursed up to 8 weeks after the humanitarian appeal date | S3.2 | 41% | 60%
| Percentage of multi-year program countries where funds were disbursed up to 6 months after the country scoping mission. | S3.3 | 0 | TBD |  |  |  | this is the standard indicator in the current results framework, but we may need to revise it as it is not realistic. Suggest to extend to "up to 6 months" and set a target of 50%
| Percentage of ECW supported multi-year programs based on a quality planning process ["quality planning process defined as: a process carried out jointly by humanitarian and development actors, evidence-based, results-based, risk informed, gender sensitive, AAP] | New indicator | TBD | TBD
| Number of joint multi-year programs developed with ECW support. | S3.4 | 6 | 8
| Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
High-level result I: Grants under the FER window are designed according to international practices and activated based on continuous analysis and assessments of major humanitarian crises triggered by natural disasters, conflict and/or epidemics
| Result 1.1: Processes for timely disbursement for FER grants are operational, and aligned to best existing practices | 1.1.1 | Streamline and strengthen grants application, appraisal, transfer, monitoring and report tracking of grants through an online interactive grants management software |  |  | X | X | X | X | Accountability, Finance and Governance
|  | 1.1.2 | Strengthen communications with OCHA and EMOPs to ensure alerts to ECW on L2 and L3 humanitarian crisis |  |  |  |  | X |  | Accountability, Finance and Governance
| Result 1.2: Quality of FER proposals aligned to achieve delivery of a decent education for all beneficiaries of FER grants | 1.2.1 | Update FER guidance to enhance the quality of interventions (ensure gender-responsive programming, MHPSS, protection, school feeding, monitoring, reporting and evaluation), and ensure development of COVID FER Template. |  |  | X | X |  |  | Education Quality/Country leads
|  | 1.2.2 | Improve quality of FERs, including COVID FERS through a robust quality assurance process |  |  | X | X |  |  | Education Quality/Country leads & Co-leads
High-level result II : MYRPs deliver quality education to all targeted children
| Result 2.1: Up to eight MYRPs are approved in 2020 [tentative list: DRC, Nigeria, Mali, Niger, Burkina Faso, Iraq, Cameroon and Venezuela response are approved in 2020] | 2.1.1 | Conduct scoping missions and establish MYRP task teams consisting of humanitarian and development actors |  |  | X | X | X |  | Education Quality/Country leads & Co-leads
|  | 2.1.2 | Ensure capacity is in place to support the development and formulation of the MYRPs and guide the in-country partners through outsourcing technical assistance, such as a roster of MYRP experts. |  |  | X | X | X | X | Education Quality/Country leads & Co-leads
|  | 2.1.3 | Ensure MYRP is linked to humanitarian and national development strategies, cluster strategies (where available), UNSDCF and other relevant policies and strategies,also including COVID strategies |  |  | X | X | X | X | Education Quality/Country leads & Co-leads
| Result 2.2: Quality of MYRP proposals aligned to achieve delivery of a quality education for all beneficiaries of MYRP grants | 2.2.1 | Finalize MYRP guidance documents, including requirements for gender-responsive programming, MHPSS, protection, school feeding, M&E, and working at the nexus between humanitarian and development assistance |  |  | X | X | X | X | Education Quality/Country leads & Co-leads
| Result 2.3: Best international practices for work at the hum/dev nexus are incorporated into MYRP design | 2.3.1 | Establish a Community of Practice to improve quality of programming at the nexus between humanitarian and development assistance |  |  |  |  | X | X | Country Co-leads
| Result 2.4: Strengthened regional responses and approaches | 2.4.1 | MYRPs for the Sahel and Venezuela Crises, and IGAD work |  |  | X | X | X | X | Education Quality/Country leads & Co-leads
Strategic Objective | Indicator name | Ref. in ECW results framework | Baseline or current status (if applicable) | Target for 2020 |  |  |  | Comments
ECW Strategic Objective 4: Strengthen Capacity to Response Strengthen individual and institutional capacity of those leading education efforts in crises and improve delivery systems | Percentage of ECW funding allocated to local and national responders as directly as possible to improve outcomes for affected people and reduce transactional costs, in accordance with the Grand Bargain commitment | S4.1 | 30% | 30%
| Percentage of countries in protracted crises targeted by ECW with policies regarding inclusion of refugees and internally displaced persons | S1.2 | TBD | TBD
| Percentage of cluster countries where cluster lead agencies have full time dedicated cluster staff (Coordinator and Information Manager) | S4.2 | 31% | 35%
| Number of children reached through ECW-supported innovations. | New indicator | N/A | TBD
| Number of ECW-supported innovations following a quality approach towards designing, testing, and scaling-up in EiE. | New indicator | N/A | TBD
| Absorptive capacity: portion of grant budgets that have been reported as spent on services delivered | S4.4 | 73.21% of planned expenditure at the date of the report for projects with at least 6 months of existence | 75%
| Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
High-level Result I: In-country capacity strengthened to enhance quality programming (on MHPSS, gender, protection and learning outcomes)
| Result 1.1: Technical capacity on MHPSS, gender, protection and holistic quality education, and coordination strengthened | 1.1.1 | MHPSS: a) Develop and implement an internal strategic approach for enhancing MHPSS across ECW’s investment b) Ensure that every MYRP and FER has a strong component and local and/ national implementing partner on MHPSS, through the proposal development and/or review proces. This also include COVID responses c) Provide technical support in the field or remotely (particularly during COVID crisis), with a focus on capacity building and mapping potential in-country MHPSS partners. d) Build a coalition of at least 3 influential MHPSS in EiE organizations, through MoUs and/or AF grants. |  |  | X |  |  |  | Quality Education / MHPSS Specialist
[6 empty] | X | X | X | X
[7 empty] | X | X
[7 empty] | X | X
|  | 1.1.2 | Gender: a) Finalize a gender resource package to address gender mainstreaming needs for grant proposals for FER and MYRP windows (by end of Q2) and roll out of the resource in the second half of the year. b) Conduct meetings (in-person or teleconference) with country Gender Focal Points/Specialists to review the implementation of the Policy and GES 2018-2021. c) Provide distance and in-country support on integration of gender and formulation of gender targeted interventions in the MYRPs and FER, including targeted support during COVID response d) Establish a community of practice |  |  | X | X | X | X | Quality Education / Gender Programme Manager, UNGEI and Plan
[9 empty] | X | ECW and MYRP partners (GFP)
[6 empty] | X | X | X | X | Quality Education / Gender Programme Manager
|  | 1.1.3 | Quality teaching and learning: a) Identify inclusive practices on teaching and learning in education in emergency contexts, including practices during COVID response b) Explore and mobilize partners to strengthen capacities at country level to support inclusive quality teaching and learning, and adapting to COVID response |  |  | X | X | X | X | M&E, DATA & Reporting/Quality Education
|  | 1.1.4 | Protection a) Ensure that every MYRP and FER proposals contain a strong component on protection, including particular attention during COVID b) Increase funding for refugee education (through COVID response) c) Contribute to protection guidelines and key messages published by the Safe To Learn Initiative |  |  | X | X | X | X | ECW and partners (UNHCR, IGAD)
|  | 1.1.5 | Holistic response to education needs: a) Finalize quality education guidance note and appraisal template; b) Support the development of quality TOCs focused on improving holistic learning outcomes |  |  | X | X | X | X | M&E, DATA & Reporting
| Result 1.2: Technical, financial and managerial capacity of Clusters/EiEWGs enhanced to lead effective education responses | 1.2.1 | a) Strengthen the capacity of Cluster/EiEWG Coordinators and Information Managers via the current grant to the GEC under the Acceleration Facility b) Advocate for funding under MYRPs for Cluster/EiEWG Coordinators and Information Managers to ensure fully staffed coordination mechanisms |  |  | X | X | X | X | ECW, Global Education Cluster
High-level Result II: Innovative products and/or services (global goods) directly support in-country capacity and quality programming
| Result 2.1: Institutional capacity of EiE networks is strengthened | 2.1.1 | Provide support to the Inter-agency Network of Education in Emergencies and the Child Protection Humanitarian Alliance | [5 empty] | X | Education Quality
| Result 2.2: Innovative solutions are scaled and reported on in selected countries or regions | 2.2.1 | a) Initiate research on how innovation can be scaled up and support a new cohort of innovations targeting MYRP countries, to include COVID related innovations b) Establish partnerships with private sector to further explore and enhance the use of technology to deliver education in emergencies, including under COVID contexts |  |  | X | X | X | X | Education Quality
Strategic Objective | Indicator name | Ref. in ECW results framework | Baseline or current status (if applicable) | Target for 2020 |  |  |  | Comments
ECW Strategic Objective 5: Improve accountability Develop and share knowledge with a focus on increasing awareness of need and evidence for effective people-centered interventions | Percentage of ECW-supported MYRPs having quality data on learning outcomes [without SEL] | New indicator | 1 out 7 MYRPs | at least 50% of MYRPs |  |  |  | All MYRPs designed in 2019 make provisions for collection of quality learning data, but not all MYRPs may have quality learning data available by Q4 2020
| Percentage of ECW-supported MYRPs having quality data on learning outcomes [including SEL] | New indicator | 0 out of 7 MYRPs | at least 40% of MYRPs |  |  |  | All MYRPs designed in 2019 make provisions for collection of quality learning data, but not all MYRPs may have quality learning data available by Q4 2020
| Percentage of ECW supported programs/of total investments with a minimum gender-age marker (GAM) score of at least 3 | New indicator | N/A | at least 50% of MYRPs
| Percentage of ECW supported MYRPs informed by quality evidence [quality elements are: timeliness, holistic scope, disaggregation, conflict/disaster sensitive, alignment, AAP] | New indicator | N/A | at least 50% of MYRPs
| Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
High level result I: ECW programs and decisions are informed by rigorous, timely data and analysis
| Result 1.1: ECW establishes and maintains a real-time crisis-monitoring system | 1.1.1 | Build a database using existing datasets on crises-severity and EiE |  |  | X |  |  |  | M&E, DATA & Reporting
|  | 1.1.2 | Establish and maintain partnerships with relevant data providers (pertaining to education in crises) |  |  | X | X | X | X | M&E, DATA & Reporting
|  | 1.1.3 | Produce briefs and communication materials to inform evidence-based advocacy |  |  | X | X | X | X | M&E, DATA & Reporting with Communication and Advocacy
| Result 1.2: Data on education needs is available for MYRP planning / design phase | 1.2.1 | Assess data gaps in MYRP countries |  |  | X | X | X | X | M&E / Country leads / MYRP partners
|  | 1.2.2 | Support targeted education needs assessments/analyses in MYRP countries |  |  | X | X | X | X | M&E / Country leads / MYRP partners
| Result 1.3: Quality control system in place to monitor integration of robust gender analysis in programming | 1.3.1 | Develop clear criteria for inclusion of mandatory and robust gender analysis within the broader needs assessment of grant proposals |  |  | X | X | X |  | M&E / Country leads / Gender and Development Manager
|  | 1.3.2 | Establish an ECW financial resource tracking mechanism to quantify disbursement of funds to programs scoring at least 3 on the GAM |  |  |  |  | X |  | M&E / Country leads / Gender and Development Manager
High level result II: Global and national capacities to generate quality data in EiE are strengthened
| Result 2.1: Tools, guidance and evidence are generated and shared (in MYRPs countries) to improve measurement of holistic learning outcomes (literacy, numeracy, social and emotional learning) | 2.1.1 | Recruit global partner and in-country grantee to facilitate 3 country case studies |  |  | X | X |  |  | M&E, Data & Reporting
|  | 2.1.2 | Conduct holistic learning outcome measurement in the chosen countries and capture lessons learnt |  |  |  | X | X |  | M&E, Data & Reporting
|  | 2.1.3 | Consolidate findings and write a white paper on holistic learning outcomes measurement in EiE | [5 empty] | X | M&E, Data & Reporting
| Result 2.2: Actionable recommendations on how to adapt EMIS in crisis settings are provided and initiatives to implement the recommendations are taken accordingly | 2.2.1 | Conduct in-country case studies and organize conference in partnership with UNESCO |  |  | X | X | X |  | M&E, Data & Reporting
|  | 2.2.2 | Develop and undertake interventions based on lessons learnt and integrate them into MYRPs | [5 empty] | X | M&E, Data & Reporting
High level result III: ECW develops and implements effective planning, monitoring, review and reporting systems
| Results 3.1: Timely compilation of data from grantees for reporting and advocacy | 3.1.1 | Update dashboard [or full database, if necessary] shared every quarter with ExCom with disaggregation of core indicators and headcount of beneficiaries by country and funding window |  |  | X | X | X | X | M&E, Data & Reporting with Communication&Advocacy
|  | 3.1.2 | Update dashboard within 30 days of receipt of reports from the grantees and published online every month |  |  | X | X | X | X | M&E, Data & Reporting with Communication&Advocacy
|  | 3.1.3 | Generate an annual report on integration of gender in ECW investments |  |  |  |  | X | X | M&E, Data & Reporting with Communication&Advocacy/Gender Manager
|  | 3.1.4 | Formulate internal GEEWG monitoring methodology and template to determine compliance with ECW Gender Policy. |  |  |  |  | X |  | M&E, Data & Reporting/Education Quality/Gender Manager
| Result 3.2: Value-for-Money analysis | 3.2.1 | Conduct cost-per-child analysis (within FER grants and within MYRP grants, and COVID FERs) |  |  | X | X | X |  | M&E, Data & Reporting
|  | 3.2.2 | Conduct VfM analysis on accelerated education [depending on availability of duly disaggregated financial data] |  |  |  | X | X | X | M&E, Data & Reporting
|  | 3.2.3 | Finalise case studies on VfM on two MYRP countries |  |  |  |  | X | X | M&E, Data & Reporting
| Result 3.3: Grantees are provided more specific guidance and tools to improve monitoring and reporting | 3.3.1 | Maintain and update library of indicators with updated guidance note |  |  | X | X | X | X | M&E, Data & Reporting
|  | 3.3.2 | Disseminate to grantees guidelines to avoid activity-based reporting |  |  | X |  |  |  | M&E, Data & Reporting / Country Leads
| Result 3.4: Annual result reports is finalised and disseminated | 3.4.1 | Collect, check and compile data, results and analysis |  |  | X |  |  |  | M&E, Data & Reporting
|  | 3.4.2 | Finalise Annual Results Report |  |  |  | X |  |  | M&E, Data & Reporting with Communication&Advocacy
High level result IV: ECW's strategies and programs are informed by rigorous, independent evaluation
| Result 4.1: Evaluation of FER funding modality is conducted and management response is approved | 4.1.1 | Establish Reference group |  |  | X | X |  |  | M&E, Data & Reporting
|  | 4.1.2 | Conduct Evaluation for FERs, to include COVID context |  |  |  | X |  |  | M&E, Data & Reporting
|  | 4.1.3 | Approve management response to the Evaluation Report |  |  |  | X | X | X | M&E, Data & Reporting
| Result 4.2: Evaluation of MYRP funding modality is conducted and management response is approved | 4.2.1 | Establish reference group |  |  |  |  | X |  | M&E, Data & Reporting
|  | 4.2.2 | Conduct Evaluation for MYRPs, to include COVID context |  |  |  |  | X | X | M&E, Data & Reporting
|  | 4.2.3 | Approve management response to the Evaluation Report | [5 empty] | X | M&E, Data & Reporting
Strategic Objective | Expected Results | # | Main Activities |  |  | Timeframe |  |  |  | ECW Lead in partnership with XX
[6 empty] | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4
Management Objective 6: ECW Secretariat fit for purpose, both in structure and transparency, to support the implementation of the Strategic Plan. Particular attention will be allocated to ensure the Secretariat is fully operational through a highly competent, multi-display team who has experience of the humanitarian-development nexus and who is able to deliver on ECW's core functions | High level result I: ECW Operates optimally through sounds system, processes and governance structure
| Result 1.1: Standards, guidelines and SoPs put in place to build effective operational and organizaiton processes | 1.1.1 | Complete SoPs with UNICEF PPD and FSO, and share with EXCOM for information |  |  | X | X |  |  | Accountability, Finance and Governance
|  | 1.1.2 | Finalize the Operations Manual |  |  | X |  |  |  | Accountability, Finance and Governance
|  | 1.1.3 | Complete appendices to the Operational manual |  |  |  | X | X | X | Accountability, Finance and Governance
|  | 1.1.4 | Finalize the Standard Contribution Agreement (SCA) |  |  |  | X |  |  | Accountability, Finance and Governance, EXCOM, FSO, UNICEF LEGAL
|  | 1.1.5 | Finalize MYRP templates and instruction, ensuring alignment with the Operations Manual |  |  |  | X |  |  | Accountability, Finance and Governance
|  | 1.1.6 | Produce Capacity Building Framework |  |  |  |  | X |  | Accountability, Finance and Governance
|  | 1.1.7 | Produce and implement SOPs for grants management, risk management (including COVID context risk matrix), Child Safeguarding, and financial monitoring |  |  |  | X | X |  | Accountability, Finance and Governance
|  | 1.1.8 | Develop an MoU with GPE |  |  |  | X |  |  | External Relations and Partnerships unit
| Result 1.2: Secretariat fully operational through a highly competent and multi-disciplinary team | 1.2.1 | Implement relocation of staff . |  |  |  | X |  |  | Accountability, Finance and Governance
|  | 1.2.2 | Implement Annual Workplan and monitor on regular basis |  |  | X | X | X | X | Accountability, Finance and Governance
|  | 1.2.3 | Identify a workable approach and procedure for taking in private sector and individual donations with UNICEF-FSO |  |  |  | X |  |  | Accountability, Finance and Governance
| Result 1.3: Risk Framework and Child Safeguarding policy integrated and kept updated at the corporate as well as at country levels | 1.3.1 | Review and update ECW Corporate Risk Framework regularly to reflect new risks, including six month updates to EXCOM |  |  | X | X | X | X | Accountability, Finance and Governance
|  | 1.3.2 | Strengthen ECW system for risk management at country level |  |  | X | X | X | X | Accountability, Finance and Governance
| Result 1.4: A gender-responsive organizational culture and practice is materialized | 1.4.1 | Ensure the alignment of Gender Equality Policy and Accountability Framework with ECW operational |  |  |  | X |  |  | Accountability, Finance and Governance / Gender Programme Manager
|  | 1.4.2 | Ensure roles and responsibilities defined in the Gender Policy and Accountability Framework are implemented and conduct on-line training courses. |  |  | X | X |  |  | Accountability, Finance and Governance / Gender Programme Manager
| Result 1.5: Strengthened financial management on the planning, administering and monitoring of overall country allocations. | 1.5.1 | Update financial reporting on regular basis |  |  | X | X | X | X | Accountability, Finance and Governance
|  | 1.5.2 | Monitor and ensure speed targets of grant development and funding disbursement (FER up to 8 weeks and MYRP up to 6 months), and COVID FERs up to 2-4 weeks |  |  | X | X | X | X | Accountability, Finance and Governance
|  | 1.5.3 | Work with FSO to identify and solve administrative barriers to ensure the speed of grant development, approval and disbursement. |  |  |  | X |  |  | Accountability, Finance and Governance
| Result 1.6: Data sharing and transparency system established | 1.6.1 | Complete ECW data sharing and transparency guidance |  |  |  | X |  |  | Accountability, Finance and Governance/Advocacy and Communication
|  | 1.6.2 | Ensure the visibility of guidance on grants proposal processes on the ECW website |  |  | X | X |  |  | Advocacy and Communication
High level result II: Effective support provided to ECW Governance bodies
| Result 1.1: Meetings of High-level Steering Group and Executive Committee well coordinated | 1.1.1 | Prepare and organize two in-person HLSG meetings |  |  |  | X | X |  | Accountability, Finance and Governance
|  | 1.1.2 | Prepare and organize two in-person EXCOM meetings, two conference calls, and ad hoc calls, as required |  |  | X | X | X | X | Accountability, Finance and Governance
| Result 1.2: Standard operating procedures and tools developed to ensure effectively working with stakeholders. | 1.2.1 | Produce SoP for effective support to ECW Governance bodies |  |  | X |  |  |  | Accountability, Finance and Governance
|  | 1.2.2. | Explore the establishment of a platform where all documents presented to ExCom can be made available |  |  |  | X |  |  | Accountability, Finance and Governance

## Lists (hidden)
Proforma Cost |  |  | Currencies | Programme Area | Report Type | Status | Status | Transparency | Location | GOE cost/ Located at | Cost | Donor Name | Donor ID | Short Name
D2 | 382041.28 | IP | USD | Please select Unit | Monthly update | Done | Not submitted | Published | East Jerusalem | Jerusalem Office | 12000 | <Donor Name> | 00000 | <Donor>
D1 | 356463.25 | IP | Euro | Infra WB | Quarterly Status Report | Partially Done | Submitted & donor requested to revise | Not Published | West Bank | Gaza Office | 14959 | UNITED NATIONS VOLUNTEERS | 00011 | UNDP(UNV)
P5 | 324185.24 | IP | NOK | Infra Gaza | Semi-annual status report | Not Done | Submitted & awaiting donor approval |  | Gaza | Project Office (J/G) | 1400 | UNITED NATIONS DEVELOPMENT PRO | 00012 | UNDP
P4 | 286380.1 | IP | NIS | Poverty | Annual Status Report | Not applicable | Submission is approved by donor |  |  |  |  | WORLD BANK (INT'L. BANK FOR RE | 00015 | IBRD
P3 | 245924.23 | IP |  | Governance | Final Report | [6 empty] | ARAB FUND FOR ECONOMIC & SOCIA | 00019 | AFESD
P2 | 211163.16 | IP |  | DPAT | [5 empty] | UNDSS | 1430 | ISLAMIC DEVELOPMENT BANK | 00020 | ISDB
P1 | 113949 | IP |  | ProgOPs | [5 empty] | SecEquip | 1736 | UNITED NATIONS POPULATION FUND | 00031 | UNFPA
NOD | 137105.26 | IP | [7 empty] | Email | 300 | UN Women | 00032 | UNWomen
NOC | 120301.76 | IP | [7 empty] | LMS | 100 | UNITED NATIONS CHILDREN'S FUND | 00035 | UNICEF
NOB | 105560.45 | IP | [9 empty] | UNOCHA | 00038 | UNOCHA
NOA | 92630.87 | IP | [9 empty] | UN HIGH COMMISSIONER FOR REFUG | 00040 | UNHCR
G7 | 93889.58 | GS | [9 empty] | UNITED NATIONS ENVIRONMENT PRO | 00041 | UNEP
G6 | 82393.17 | GS |  | IP / Agency Type | Agreement Amendment |  | Source of income by funding stream |  |  |  |  | GOVERNMENT OF BELGIUM | 00061 | BEL
G5 | 72944.1 | GS |  | Govt | No-Cost extension |  | Government Cost Sharing |  |  |  |  | GOVERNMENT OF ITALY | 00137 | ITA
G4 | 64583.78 | GS |  | CSO | Cost extension |  | Donor cost sharing |  |  |  |  | GOVERNMENT OF JAPAN | 00141 | JPN
G3 | 57184.36 | GS |  | NGO (INTL) | Additional Contribution |  | EC cost sharing |  |  |  |  | GOVERNMENT OF NETHERLANDS | 00182 | NET
G2 | 50636.49 | GS |  | NGO (NATL) |  |  | Global Fund |  |  |  |  | GOVERNMENT OF NORWAY | 00187 | NOR
G1 | 44841.49 | GS |  | Other |  |  | GEF |  |  |  |  | GOVERNMENT OF NEW ZEALAND | 00188 | NZE
SB1/1 | 19973.4569 | SC |  |  |  |  | Montreal Protocol |  |  |  |  | State of Palestine | 00191 | PAL
SB1/2 | 22800.0404 | SC |  |  |  |  | South-South cost sharing |  |  |  |  | GOVERNMENT OF SAUDI ARABIA | 00210 | SAU
SB1/3 | 25626.309 | SC |  |  |  |  | Trust Fund |  |  |  |  | GOVERNMENT OF SPAIN | 00220 | SPA
SB1/4 | 28452.8924 | SC |  |  |  |  | Funding window |  |  |  |  | GOVERNMENT OF UNITED STATES OF | 00253 | USA
SB1/5 | 31279.161 | SC |  |  |  |  | GCF |  |  |  |  | EUROPEAN UNION | 00280 | EU
SB2/1 | 27105.251 | SC | [9 empty] | GLOBAL FUND TO FIGHT AIDS, TUB | 00327 | GFATM
SB2/2 | 30509.9348 | SC | [9 empty] | CANADIAN INTERNATIONAL DEVELOP | 00550 | CIDA
SB2/3 | 33914.9336 | SC | [9 empty] | DEPARTMENT FOR INT'L DEVELOPME | 00551 | DFID
SB2/4 | 37319.9323 | SC |  | Procurement_Type | Civil_Works | Goods | Individual_Consultant | Services |  |  |  | SWEDISH INT'L DEVELOPMENT COOP | 00555 | SIDA
SB2/5 | 40724.9311 | SC |  | Civil_Works | Construction - Horizontal (Roads, canals, etc.) | Armoured Vehicles | Individual Consultants - International | Audit Services |  |  |  | The Republic of Korea | 00717 | C/S-ROK
SB3/1 | 35842.8795 | SC |  | Goods | Construction - Vertical (Buildings, etc.) | Computer Software | Individual Consultants - National | Cleaning Services |  |  |  | EUROPEAN COMMISSION | 10159 | EUCOMM
SB3/2 | 41786.0413 | SC |  | Individual_Consultant | Rehabilitation of Infrastructure | Contraceptives |  | Communication/Advocacy Services |  |  |  | UNSCO, GAZA | 10188 | UNSCO, GAZ
SB3/3 | 47729.203 | SC |  | Services |  | Drugs and Pharmaceuticals |  | Consultancy Services - Firms |  |  |  | SWISS AGY FOR DEVELOPMENT & CO | 10282 | SDC
SB3/4 | 53672.3647 | SC |  |  |  | Election Items |  | NGO/CSO Engagement |  |  |  | KREDITANSTALT FUR WIEDERAUFBAU | 10283 | KFW
SB3/5 | 59615.5265 | SC |  | Status |  | Electronic Hardware - non-ICT |  | Office/Warehouse Lease Agreements |  |  |  | UN RELIEF AND WORKS AGENCY | 10334 | UNRWA
SB4/1 | 47845.0486 | SC |  | Planning |  | Fuel |  | Other Services |  |  |  | MINISTRY OF COMMERCE, CHINA | 10392 | MOFCOM
SB4/2 | 53184.4845 | SC |  | Requisition |  | Furniture and Fixtures |  | Port/Custom Clearing Services |  |  |  | USAID | 10480 | USAID
SB4/3 | 58523.9204 | SC |  | Bidding |  | Generators |  | Printing/Publishing and Design |  |  |  | SAUDI COMMITEE FOR PP RELIEF | 10639 | SAUDI CRPP
SB4/4 | 63863.0483 | SC |  | Evaluation |  | ICT Equipment |  | Rent/Lease of Vehicles |  |  |  | ICELAND - MIN. FOREIGN AFFAIRS | 10994 | ICEMINFORA
SB4/5 | 69202.4843 | SC |  | PRC Review |  | Medical and laboratory Equipment/Supplies |  | Security Services |  |  |  | OPEC Fund for International De | 11120 | OPEC Fund
SB5/1 | 60173.0315 | SC |  | Contracted |  | Meteorological Equipment |  | Software Development |  |  |  | Italian Min. for Foreign Affai | 11227 | ITA MAE
SB5/2 | 67971.3493 | SC |  |  |  | Motor Vehicles and Parts |  | Translation Services (by Companies) |  |  |  | Austrian Development Agency | 11266 | ADA
SB5/3 | 75769.9751 | SC |  | Duration |  | Office Supplies |  | Transport and Storage Services |  |  |  | UNOCHA/Central_Emg_Resp_Fund | 11362 | CERF
SB5/4 | 83568.2929 | SC |  | Day(s) |  | Other Goods |  | Travel/Events/Catering |  |  |  | Adam Smith International | 12000 | ASI
SB5/4 | 91366.9187 | SC |  | Week(s) |  | Pesticides/Herbicides |  | Vehicle Maintenance |  |  |  | The paltel group Foundation | 12072 | paltel
GP | 22274 | GP |  | Month(s) |  | Phone/VHF/HF Equipment |  | Workshop/Seminar Cost (Location and/or Catering) |  |  |  | Royal Charity Org. Bahrain | 12101 | RCO
|  |  |  | Year(s) |  | Pre-fabricated Buildings | [5 empty] | The Department of Foreign Affa | 12113 | DFATD
[6 empty] | Printers and Copiers | [5 empty] | Education Above All-AlFakhoora | 12253 | EAAFakhoor
[6 empty] | Renewable Energy Equipment (Solar Panels, etc.) | [5 empty] | MDTFO JP oPt Rule of Law | 12256 | MDTFO oPtR
[6 empty] | Rent/Lease of Copiers or ICT Equipment | [5 empty] | Bank of Palestine | 12513 | Bk. of PAL
[6 empty] | Safety and Security Equipment | [5 empty] | Islamic Relief Canada | 12565 | IRC
[6 empty] | Textiles and/or Footwear | [5 empty] | GOVERNMENT OF AUSTRALIA | 00055 | AUL
Waste Management

## Projlst (hidden)
Unit | Output | Output | Output Description | Project | Project Descr | Thematic Unit | Output Status | Start Date | End Date | Project Status | Days Passed | Months Passed
ENV | 00082361 | 82361 | Mainstreaming Climate Change | 66131 | Low carbon development and climate change resilient Prog | Environment & Natural Resources | On Going | 2013-05-03 | 2017-12-31 | Agreement Ended | 12 | 0
ENV | 00086815 | 86815 | Hydro Climate Modeling | 66131 | Low carbon development and climate change resilient Prog | Environment & Natural Resources | On Going | 2014-01-01 | 2017-12-31 | Agreement Ended | 12 | 0
ENV | 00088464 | 88464 | Disaster Risk Reduction | 77909 | Resilience Against Natural Disasters â€œRANDâ€ | Environment & Natural Resources | On Going | 2014-01-02 | 2017-12-31 | Agreement Ended | 12 | 0
Gov | 00014145 | 14145 | JAPANESE ENDOWMENT FUND | 14145 | JAPANESE ENDOWMENT FUND | Governance & Social Development | On Going | 1901-01-01 | 2018-11-30 | Valid Agreement
Gov | 00084013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM | Governance & Social Development | On Going | 2012-06-01 | 2018-03-31 | Valid Agreement
Gov | 00088270 | 88270 | Capacity of Justice & Security | 77565 | Strengthen ROL 2nd phase in OPT | Governance & Social Development | On Going | 2014-01-01 | 2017-12-31 | Agreement Ended | 12 | 0
Gov | 00098489 | 98489 | BUILDING A SUSTAINABLE LEGAL A | 77565 | Strengthen ROL 2nd phase in OPT | Governance & Social Development | On Going | 2016-01-01 | 2017-12-31 | Agreement Ended | 12 | 0
Gov | 00092109 | 92109 | National and Social Cohesion | 83801 | Palestinian National Unity and Social Cohesion Programme | Governance & Social Development | On Going | 2014-10-20 | 2017-12-31 | Agreement Ended | 12 | 0
Gov | 00105560 | 105560 | OQ Rule of Law | 47872 | Support to the Office of the Quartet Representative | Governance & Social Development | On Going | 2017-03-01 | 2018-02-28 | Valid Agreement
Gov | 00105165 | 105165 | Sawasya II inception phase | 77565 | Strengthen ROL 2nd phase in OPT | Governance & Social Development | On Going | 2017-05-01 | 2018-12-31 | Valid Agreement
Gov | 00102744 | 102744 | Empowering Youth | 99465 | Emergency Response to Palestinian Youth Despair | Governance & Social Development | On Going | 2017-01-01 | 2018-12-31 | Valid Agreement
IG | 00047395 | 47395 | Construction of TreatmentPlant | 41529 | Construction of Sewage Treatment Plant in Khan Younis | Infrastructure Gaza | On Going | 2005-08-01 | 2018-06-30 | Valid Agreement
IG | 00049740 | 49740 | Const.of 300 Residential Units | 42831 | PAL/ Construction of 300 Housing Units in Rafah | Infrastructure Gaza | On Going | 2006-01-01 | 2017-09-30 | Agreement Ended | 104 | 3
IG | 00099288 | 99288 | Repair of damaged Non-Refugee | 42831 | PAL/ Construction of 300 Housing Units in Rafah | Infrastructure Gaza | On Going | 2016-03-16 | 2018-07-14 | Valid Agreement
IG | 00092145 | 92145 | Emergency Cash Assistance Sida | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza | Infrastructure Gaza | On Going | 2014-10-09 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00092457 | 92457 | Re-construction of houses | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza | Infrastructure Gaza | On Going | 2014-11-02 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00070416 | 70416 | Construction of 100 Housing Un | 57098 | Construction of 100 Housing Units | Infrastructure Gaza | On Going | 2009-04-01 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00094505 | 94505 | Reconstruction works for Atta | 66569 | Rehabilitation and Reconstruction of health premises | Infrastructure Gaza | On Going | 2015-03-12 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00094739 | 94739 | Right to Education in Gaza | 87840 | Right to Education in the Gaza Strip | Infrastructure Gaza | On Going | 2015-02-12 | 2018-03-31 | Valid Agreement
IG | 00096413 | 96413 | Periodic Maintenance of School | 87840 | Right to Education in the Gaza Strip | Infrastructure Gaza | On Going | 2015-04-01 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00096619 | 96619 | Renewable energy for All â€“ Gaz | 91323 | Renewable energy for All â€“ Gaza Strip | Infrastructure Gaza | On Going | 2015-05-01 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00098764 | 98764 | Energy networks recovered | 94677 | Rehabilitation of Electricity Power Distribution Network | Infrastructure Gaza | On Going | 2016-03-01 | 2017-12-31 | Agreement Ended | 12 | 0
IG | 00102677 | 102677 | Early recovery for Economy | 99398 | Rehabilitation & Construction of Gaza Industrial Estate | Infrastructure Gaza | On Going | 2017-01-01 | 2018-08-31 | Valid Agreement
IW | 00046774 | 46774 | Small Scale Works&Employment 5 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2006-05-08 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00060764 | 60764 | Small Scale Works&Employment 6 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2008-07-01 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00073017 | 73017 | Small Scale Works&Employment 7 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2010-01-01 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00080762 | 80762 | Small Scale Works&Employment 8 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2012-01-01 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00086843 | 86843 | Small Scale Works&Employment 9 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2013-06-06 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00093278 | 93278 | Small Scale Works Employment10 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII | Infrastructure W.B. | On Going | 2014-11-12 | 2018-06-30 | Valid Agreement
IW | 00077024 | 77024 | Hebron Courthouse Building | 57409 | Supporting the Rule of Law and Access to Justice | Infrastructure W.B. | On Going | 2011-01-01 | 2019-12-31 | Valid Agreement
IW | 00087560 | 87560 | Capacity Developmnt Support P1 | 58277 | P1 - Construction of the Jericho Agro-Industrial Park | Infrastructure W.B. | On Going | 2013-09-01 | 2018-02-28 | Valid Agreement
IW | 00094430 | 94430 | Capacity Development Support | 58277 | P1 - Construction of the Jericho Agro-Industrial Park | Infrastructure W.B. | On Going | 2015-03-04 | 2018-12-31 | Valid Agreement
IW | 00084404 | 84404 | Jerusalem Shops Rehabilitation | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK | Infrastructure W.B. | On Going | 2012-11-01 | 2018-06-30 | Valid Agreement
IW | 00086299 | 86299 | Homes Rehabilitation Phase II | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK | Infrastructure W.B. | On Going | 2013-04-19 | 2017-12-20 | Agreement Ended | 23 | 0
IW | 00086777 | 86777 | Cultural Heritage Safeguarding | 74323 | Safeguarding of Cultural Heritage in the Old City | Infrastructure W.B. | On Going | 2013-06-15 | 2017-08-25 | Agreement Ended | 140 | 4
IW | 00087760 | 87760 | Right to Education | 75685 | FAIR-Facilitating Access to Infrastructure Resilience | Infrastructure W.B. | On Going | 2013-09-24 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00090824 | 90824 | Resilience&Access Facilitation | 75685 | FAIR-Facilitating Access to Infrastructure Resilience | Infrastructure W.B. | On Going | 2014-06-11 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00097586 | 97586 | Access to Cancer Care in Jerus | 75685 | FAIR-Facilitating Access to Infrastructure Resilience | Infrastructure W.B. | On Going | 2015-12-22 | 2018-12-31 | Valid Agreement
IW | 00088974 | 88974 | Development Cultural Tourism | 78870 | Support to Development of Cultural Tourism | Infrastructure W.B. | On Going | 2014-01-01 | 2018-12-31 | Valid Agreement
IW | 00094529 | 94529 | Support Employment Generation | 87577 | Support to Employment Generation | Infrastructure W.B. | On Going | 2015-04-15 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00094044 | 94044 | Productivity&Urban Renewal JRS | 87585 | Productivity and Urban Renewal in East Jerusalem | Infrastructure W.B. | On Going | 2015-02-06 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00106598 | 106598 | Support to Edu Sector in EJ | 75685 | FAIR-Facilitating Access to Infrastructure Resilience | Infrastructure W.B. | On Going | 2017-08-07 | 2018-08-07 | Valid Agreement
IW | 00104547 | 104547 | Ph II Levelling & Well | 87577 | Support to Employment Generation | Infrastructure W.B. | On Going | 2017-03-23 | 2018-03-31 | Valid Agreement
IW | 00104548 | 104548 | JAIP Solid Waste Mangmt System | 87577 | Support to Employment Generation | Infrastructure W.B. | On Going | 2017-03-05 | 2018-06-30 | Valid Agreement
IW | 00102665 | 102665 | Support to Al Quds University | 99388 | Support to Jerusalem based institutions | Infrastructure W.B. | On Going | 2017-01-01 | 2019-12-31 | Valid Agreement
IW | 00102747 | 102747 | OFID House Rehabilitation II | 99470 | House Rehabilitation II | Infrastructure W.B. | On Going | 2016-10-21 | 2017-12-31 | Agreement Ended | 12 | 0
IW | 00103834 | 103834 | Supprt New Schools E Jerusalem | 99487 | Provision of social services in West Bank and Jerusalem | Infrastructure W.B. | On Going | 2016-11-23 | 2020-12-31 | Valid Agreement
IW | 00103835 | 103835 | Support to Health Sector in WB | 99487 | Provision of social services in West Bank and Jerusalem | Infrastructure W.B. | On Going | 2016-11-23 | 2019-12-31 | Valid Agreement
IW | 00104005 | 104005 | Support Housing in E.Jerusalem | 99487 | Provision of social services in West Bank and Jerusalem | Infrastructure W.B. | On Going | 2016-11-23 | 2020-11-22 | Valid Agreement
MSU | 00052919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP | MSU | On Going | 2006-08-17 | 2017-12-31 | Agreement Ended | 12 | 0
MSU | 00089658 | 89658 | Advocacy &knowledge production | 79772 | Knowledge Management for Advocacy | MSU | On Going | 2014-03-17 | 2017-12-31 | Agreement Ended | 12 | 0
OPR | 00020377 | 20377 | PAPP UNDSS Security | 20377 | Security | Operations | On Going | 2004-01-01 | 2020-12-31 | Valid Agreement
OPR | 00037867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY | Operations | On Going | 2004-06-14 | 2020-12-31 | Valid Agreement
OPR | 00040830 | 40830 | PAPP UNMSM Project | 37315 | TAR/ MOSS | Operations | On Going | 2004-11-01 | 2018-12-31 | Valid Agreement
OPR | 00049332 | 49332 | Programme Effectiveness - Deve | 42633 | Management Plan | Operations | On Going | 2006-01-01 | 2025-12-31 | Valid Agreement
OPR | 00049333 | 49333 | Programme Effectiveness - Know | 42633 | Management Plan | Operations | On Going | 2006-01-01 | 2025-12-31 | Valid Agreement
OPR | 00049334 | 49334 | Organizational Effectiveness | 42633 | Management Plan | Operations | On Going | 2006-01-01 | 2025-12-31 | Valid Agreement
OPR | 00056284 | 56284 | PAL-UN - Special Co-ordinator | 47037 | UN - Special Co-ordinator | Operations | On Going | 2007-04-01 | 2020-12-31 | Valid Agreement
OPR | 00061703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES | Operations | On Going | 2008-04-01 | 2017-12-31 | Agreement Ended | 12 | 0
OPR | 00081280 | 81280 | DEVELOPMENT EFFECTIVENESS DE | 64505 | DEVELOPMENT EFFECTIVENESS DE | Operations | On Going | 2012-01-01 | 2024-12-31 | Valid Agreement
POV | 00076689 | 76689 | FAKHOORA1/Dynamic Futures-Edu1 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP | Poverty Reduction Team | On Going | 2010-11-11 | 2017-12-31 | Agreement Ended | 12 | 0
POV | 00086176 | 86176 | DEEP II-Microfin&EconGrants2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP | Poverty Reduction Team | On Going | 2013-04-04 | 2020-12-31 | Valid Agreement
POV | 00091584 | 91584 | FAKHOORA II/DynamicFuturesEdu2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP | Poverty Reduction Team | On Going | 2014-08-18 | 2021-12-31 | Valid Agreement
POV | 00094477 | 94477 | SWISS-YOUTH EMPLOY GENERATIO-G | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP | Poverty Reduction Team | On Going | 2015-03-11 | 2018-12-31 | Valid Agreement
POV | 00077569 | 77569 | Land Development Jerusalem | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK | Poverty Reduction Team | On Going | 2011-01-01 | 2018-12-31 | Valid Agreement
POV | 00077570 | 77570 | Support to CSOs in EJ | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK | Poverty Reduction Team | On Going | 2011-01-01 | 2018-12-31 | Valid Agreement
POV | 00079215 | 79215 | Small Enterprises Jerusalem | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK | Poverty Reduction Team | On Going | 2011-06-15 | 2018-12-31 | Valid Agreement
POV | 00100915 | 100915 | LAND RECLAMATION & CB MOA | 96078 | LAND & AGRICULTURE & IRRIGATION | Poverty Reduction Team | On Going | 2016-06-15 | 2018-12-31 | Valid Agreement
POV | 00100082 | 100082 | JAIP/BUSINESS DEV CONSULT-SERV | 96081 | BUSINESS DEVELOPMENT CONSULTING SERVICES | Poverty Reduction Team | On Going | 2017-01-01 | 2018-12-31 | Valid Agreement
PMO | 00087068 | 87068 | Medical Procurement for Gaza | 74904 | Procurement of Drugs to Gaza | Programme Managed by Operations | On Going | 2013-06-01 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00040513 | 40513 | Support to Communication | 37063 | PAL - Support to Communications | Programme Managed by Operations | On Going | 2004-10-22 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00097401 | 97401 | Resident Coordinator Admin | 47037 | UN - Special Co-ordinator | Programme Managed by Operations | On Going | 2015-12-10 | 2018-03-31 | Valid Agreement
PMO | 00058778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative | Programme Managed by Operations | On Going | 2007-08-01 | 2017-03-31 | Agreement Ended | 287 | 9
PMO | 00062844 | 62844 | Quartet-Blair Mission DOS | 47872 | Support to the Office of the Quartet Representative | Programme Managed by Operations | On Going | 2008-09-18 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00086407 | 86407 | OQR-Dutch | 47872 | Support to the Office of the Quartet Representative | Programme Managed by Operations | On Going | 2013-04-01 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00097218 | 97218 | Office of Quartet Gas for Gaza | 47872 | Support to the Office of the Quartet Representative | Programme Managed by Operations | On Going | 2015-12-01 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00093791 | 93791 | PALESTINIAN NEGOTIATIONS | 59876 | Peace Building in the oPt | Programme Managed by Operations | On Going | 2015-01-22 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00076892 | 76892 | Access Coordination and Monito | 60907 | Access Coordination and Monitoring Support | Programme Managed by Operations | On Going | 2010-10-18 | 2017-12-31 | Agreement Ended | 12 | 0
PMO | 00104517 | 104517 | UN SUPPORT adhoc liason com. | 47037 | UN - Special Co-ordinator | Programme Managed by Operations | On Going | 2017-03-01 | 2020-02-29 | Valid Agreement
PMO | 00106109 | 106109 | LACS PROJECT | 47037 | UN - Special Co-ordinator | Programme Managed by Operations | On Going | 2017-07-01 | 2020-06-30 | Valid Agreement
PMO | 00105971 | 105971 | OQ Movement and Trade - Dutch | 47872 | Support to the Office of the Quartet Representative | Programme Managed by Operations | On Going | 2017-06-20 | 2017-12-31 | Agreement Ended | 12 | 0
SRT | 00072955 | 72955 | UN Early Recovery Coordination | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza | SRAT | On Going | 2009-11-19 | 2017-12-31 | Agreement Ended | 12 | 0

## Tmp (hidden)
| Output | Output Descr | Project | Project Descr
14130 | 14130 | Local Elections Support | 14130 | SUPPORT FOR ELECTIONS IN WEST BANK AND GAZA
14145 | 14145 | JAPANESE ENDOWMENT FUND | 14145 | JAPANESE ENDOWMENT FUND
14146 | 14146 | JERICHO & HEBRON WATER | 14146 | JERICHO & HEBRON WATER
14146 | 14146 | JERICHO & HEBRON WATER | 14146 | JERICHO & HEBRON WATER
14161 | 14161 | CONSTRUCTION OF GAZA AIRPORT | 14161 | CONS. EQUIP. GAZA - INTERN. AIRPORT
14162 | 14162 | TECHNICAL ASSITANCE &EQUIPMENT | 14162 | TECHNICAL ASSITANCE & EQUIPMENT- GAZA AIR PORT
14163 | 14163 | Dev. of Alia Hos. North Wing | 14163 | Development of the Northern Wing at Alia Hospital
14169 | 14169 | LOCAL RURAL DEVELOPMENT PHASE | 14169 | LOCAL RURAL DEVELOPMENT PHASE III
14169 | 14169 | LOCAL RURAL DEVELOPMENT PHASE | 14169 | LOCAL RURAL DEVELOPMENT PHASE III
14172 | 14172 | URGENT WATER SUPPLY TO UN-SERV | 14172 | URGENT WATER SUPPLY TO UN-SERVED AREAS OF- WB
14179 | 14179 | Contruction of Tulkarem Hosp. | 14179 | Construction of the Tulkarem Gov. Hospital - Phase III
14183 | 14183 | PARTICIPATORY NATURAL RESOURCE | 14183 | Participatory Natural Resources Management
14193 | 14193 | Rehabilitation of HEALTH; EDU | 14193 | Rehabilitation of HEALTH; EDUC - IDB
14201 | 14201 | Salfeet Hospital Construction | 14201 | Construction of the Salfeet Government Hospital
14202 | 14202 | Finnishing Works:Civil Affairs | 14202 | Finishing Ministry of Interior - IT & Civilian Unit
14205 | 14205 | ILO Vocational Rehb Cntr | 14205 | Vocational Rehabilitation Center - ILO
20377 | 20377 | PAPP UNDSS Security | 20377 | Security
20377 | 20377 | PAPP UNDSS Security | 20377 | Security
83039 | 83039 | UNV/Mgmt Field Unit Equipment | 31349 | Support for Programme Development and Operations
36456 | 36456 | DSS HQ component of FSO budget | 34377 | UNSECOORD's HQ component of FSO support budget
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
37867 | 37867 | DPCA - SECURITY | 35321 | DPCA - SECURITY
38745 | 38745 | Emergency Infrastructure Works | 35887 | Emergency Humanitarian Infra. Relief Programme ( CAP I)
38746 | 38746 | Emergency Small Scale Projects | 35888 | Emergency Small Scale Projects
38750 | 38750 | TOKTEN; Sup. streng. PA inst. | 35893 | Support to Strengthining the PA institutions;TOKTEN
38824 | 38824 | Local Governance Reform | 35946 | Support to Local Govt. Reforms- Legal Framework ;CB
40513 | 40513 | Support to Communication | 37063 | PAL - Support to Communications
40732 | 40732 | Â Automation: Justice Sector | 37229 | PAL/ Support to Judiciary and Rule of Law
40732 | 40732 | Â Automation: Justice Sector | 37229 | PAL/ Support to Judiciary and Rule of Law
40830 | 40830 | PAPP UNMSM Project | 37315 | TAR/ MOSS
40830 | 40830 | PAPP UNMSM Project | 37315 | TAR/ MOSS
41156 | 41156 | Small Scale Works&Employment 3 | 37586 | PAL/ Poverty Oriented Infras;Emp; KFW III - WB
41156 | 41156 | Small Scale Works&Employment 3 | 37586 | PAL/ Poverty Oriented Infras;Emp; KFW III - WB
41156 | 41156 | Small Scale Works&Employment 3 | 37586 | PAL/ Poverty Oriented Infras;Emp; KFW III - WB
41156 | 41156 | Small Scale Works&Employment 3 | 37586 | PAL/ Poverty Oriented Infras;Emp; KFW III - WB
41302 | 41302 | PAL/ Support to E&HE - KOICA I | 37699 | PAL/ Support to Education & Higher Education (KOICA I)
42946 | 42946 | PAL / TOKTEN - Phase VI | 38626 | PAL / TOKTEN - Phase VI
43670 | 43670 | Rehabilitation of Munipalities | 39093 | PAL/ Rehbilitation of Municipal Infrastructure- CAP II
43734 | 43734 | Supp. to Pal. Educ. Programme | 39137 | SPEP- Support to the Palestinain Education Programme
43767 | 43767 | PAL/Emergency Humanitarian Aid | 39163 | PAL/Emergency Humanitarian Aid- Internal Roads-CAPII
43772 | 43772 | PAL/ Emergency Humanitarian Ai | 39168 | PAL/ Emergency Humanitarian Aid- WATER - CAP II
44415 | 44415 | Support LG Reform-property tax | 39552 | Support to Local Govt. Reform- Property Tax Reform
46774 | 46774 | Small Scale Works&Employment 5 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
60764 | 60764 | Small Scale Works&Employment 6 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
73017 | 73017 | Small Scale Works&Employment 7 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
80762 | 80762 | Small Scale Works&Employment 8 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
86843 | 86843 | Small Scale Works&Employment 9 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
93278 | 93278 | Small Scale Works Employment10 | 41098 | Poverty Oriented Infrastructure thru EPG'S - KFW V-VII
47076 | 47076 | CAP II Schools | 41326 | Emergency Humanitarian Aid- Schools CAP II
47106 | 47106 | PAL/ Improvement of Medical Wa | 41346 | PAL/ Improvement of Medical Waste Management in Ramallah
47106 | 47106 | PAL/ Improvement of Medical Wa | 41346 | PAL/ Improvement of Medical Waste Management in Ramallah
47232 | 47232 | tPAL/ Construction & Equipping | 41443 | PAL/Construction & Equipping of the First Instance Court
47234 | 47234 | PAL/ Provision of Reliable Wat | 41445 | ALLAR & SAIDA - Provision of Reliable Water Supply
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
47296 | 47296 | PAL/ UNV- Reform Intervention | 41489 | PAL/ UNV- Reform Intervention Programme
70291 | 70291 | UNV-OCHA | 41489 | PAL/ UNV- Reform Intervention Programme
70293 | 70293 | UNV-SHAREK | 41489 | PAL/ UNV- Reform Intervention Programme
47298 | 47298 | PAL/ Provision of Reliable Wat | 41491 | PAL/ Provision of Reliable Water Supply to ZBUBA
47393 | 47393 | Construction of 200 units | 41527 | PAL/ Construction of Demolished Homes for NON REFUGEE
47395 | 47395 | Construction of TreatmentPlant | 41529 | Construction of Sewage Treatment Plant in Khan Younis
47395 | 47395 | Construction of TreatmentPlant | 41529 | Construction of Sewage Treatment Plant in Khan Younis
47395 | 47395 | Construction of TreatmentPlant | 41529 | Construction of Sewage Treatment Plant in Khan Younis
48456 | 48456 | Participatory Rural Planning | 42278 | PAL/ Participatory Rural Planning & Development (jenin)
48456 | 48456 | Participatory Rural Planning | 42278 | PAL/ Participatory Rural Planning & Development (jenin)
49332 | 49332 | Programme Effectiveness - Deve | 42633 | Management Plan
49333 | 49333 | Programme Effectiveness - Know | 42633 | Management Plan
49334 | 49334 | Organizational Effectiveness | 42633 | Management Plan
49334 | 49334 | Organizational Effectiveness | 42633 | Management Plan
49334 | 49334 | Organizational Effectiveness | 42633 | Management Plan
49334 | 49334 | Organizational Effectiveness | 42633 | Management Plan
49740 | 49740 | Const.of 300 Residential Units | 42831 | PAL/ Construction of 300 Housing Units in Rafah
49740 | 49740 | Const.of 300 Residential Units | 42831 | PAL/ Construction of 300 Housing Units in Rafah
99288 | 99288 | repair damaged housing units | 42831 | PAL/ Construction of 300 Housing Units in Rafah
51268 | 51268 | On-the-job-training for unempl | 43808 | On-the-job-training for unemployed youth
51268 | 51268 | On-the-job-training for unempl | 43808 | On-the-job-training for unemployed youth
51843 | 51843 | DEEP I- Microfin&Econ Grants1 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
51843 | 51843 | DEEP I- Microfin&Econ Grants1 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
57920 | 57920 | PYU | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
57924 | 57924 | PADR | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
57929 | 57929 | UAWC | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
74392 | 74392 | Economic Empowerment 1 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
76689 | 76689 | FAKHOORA1/Dynamic Futures-Edu1 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
77575 | 77575 | SOCIAL DEVELOPMENT-JAPAN | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
80331 | 80331 | MICROFINANCE-NEWZEALAND | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
85135 | 85135 | Women Entrepreneurs/ DEEP-WE | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
86176 | 86176 | DEEP II-Microfin&EconGrants2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
86176 | 86176 | DEEP II-Microfin&EconGrants2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
86176 | 86176 | DEEP II-Microfin&EconGrants2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
88802 | 88802 | Microfinance - Agriculture Â | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
90491 | 90491 | AFESD 2-Economic Empowerment 2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
91584 | 91584 | FAKHOORA II/DynamicFuturesEdu2 | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
94477 | 94477 | SWISS-YOUTH EMPLOY GENERATIO-G | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
97578 | 97578 | OFID YOUTH EMPLOYMENT CREATION | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
99837 | 99837 | JapanYOUTH EMPLOYABILITY PROTc | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
101035 | 101035 | GL MAPPING STRATEGIC PLANNING | 44201 | DEPRIVED FAMILIES ECONOMIC EMPOWERMENT PROGRAMME DEEP
52402 | 52402 | Avian Flu Response | 44516 | PAL/ AVAIN FLU RESPONCE- Norway
52402 | 52402 | Avian Flu Response | 44516 | PAL/ AVAIN FLU RESPONCE- Norway
52737 | 52737 | Emergency Water Supply | 44759 | Emergency Water Supply and Rehabilitation Programme
52741 | 52741 | Empl. Generation through Emerg | 44762 | Empl. Generation through Emergency Support to SWM in GS
52847 | 52847 | Improvement of Solid Waste Man | 44825 | Improvement of Solid waste Management In the oPt
52847 | 52847 | Improvement of Solid Waste Man | 44825 | Improvement of Solid waste Management In the oPt
52919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP
52919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP
52919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP
52919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP
52919 | 52919 | PAL/ Seeds for Development Str | 44878 | PAL/ Seeds for Development Strategy Formulated for PAPP
53403 | 53403 | AVIAN FLU PREVENTION-WORLDBANK | 45243 | PAL/ Avian Influenza Prevention and control-TF057369
53403 | 53403 | AVIAN FLU PREVENTION-WORLDBANK | 45243 | PAL/ Avian Influenza Prevention and control-TF057369
54031 | 54031 | Rehab. of Destroyed Bridges | 45689 | Rehabilitation of Destroyed Bridges in the Gaza Strip
54052 | 54052 | Peace Initiative in Governance | 45709 | Support to peace initiatives in Local Governance-MAP
54446 | 54446 | UAE Housing Project in the WB | 45955 | UAE Housing Project in the West Bank
54661 | 54661 | Civil Srvs LeadershipDev. Prog | 46066 | Civil Service Leadership Development Programme(GPC)
54948 | 54948 | Export DevelopmentÂ 2 | 46247 | PAL - Brucellosis Control Project II - Spain
55072 | 55072 | Sup. to Office of President II | 46310 | Support to the Presidents Office Phase II
55072 | 55072 | Sup. to Office of President II | 46310 | Support to the Presidents Office Phase II
55072 | 55072 | Sup. to Office of President II | 46310 | Support to the Presidents Office Phase II
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
55098 | 55098 | Volunteers for Development | 46328 | PAL/ Voulnteers for Development (TOKTEN)
56067 | 56067 | Employ. Generation thru Rehab. | 46886 | Employ. Generation thru Rehab. of Agr. Facilities in GS
56284 | 56284 | RCO STAFF | 47037 | UN - Special Co-ordinator
56284 | 56284 | RCO STAFF | 47037 | UN - Special Co-ordinator
74293 | 74293 | MAXIMIZING IMPACT - UNSCO | 47037 | UN - Special Co-ordinator
74293 | 74293 | MAXIMIZING IMPACT - UNSCO | 47037 | UN - Special Co-ordinator
97401 | 97401 | Resident Coordinator Admin | 47037 | UN - Special Co-ordinator
104517 | 104517 | UN SUPPORT adhoc liason com. | 47037 | UN - Special Co-ordinator
106109 | 106109 | LACS PROJECT | 47037 | UN - Special Co-ordinator
56906 | 56906 | Emergency Assistance to Civil | 47388 | Emergency Support to Civil Society
56906 | 56906 | Emergency Assistance to Civil | 47388 | Emergency Support to Civil Society
57403 | 57403 | Community-Based Women Empowerm | 47623 | Community-Based Women Empowerment in Gaza
57403 | 57403 | Community-Based Women Empowerm | 47623 | Community-Based Women Empowerment in Gaza
57544 | 57544 | AFD Mental Health | 47717 | AFD Mental Health
57665 | 57665 | INTEGRATED RURAL DEVELOPMENT | 47798 | Integrated Rural Development
57773 | 57773 | Quartet-Blair Mission Norway | 47872 | Support to the Office of the Quartet Representative
57773 | 57773 | Quartet-Blair Mission Norway | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
58778 | 58778 | Quartet-Blair Mission DFID | 47872 | Support to the Office of the Quartet Representative
61591 | 61591 | Quartet-Blair Mission EC | 47872 | Support to the Office of the Quartet Representative
62844 | 62844 | Quartet-Blair Mission DOS | 47872 | Support to the Office of the Quartet Representative
77164 | 77164 | Blair Mission EC- 2011 | 47872 | Support to the Office of the Quartet Representative
81332 | 81332 | OQR - EC 2012 | 47872 | Support to the Office of the Quartet Representative
86407 | 86407 | OQR-Dutch | 47872 | Support to the Office of the Quartet Representative
87482 | 87482 | QUARTET - Canada | 47872 | Support to the Office of the Quartet Representative
89295 | 89295 | OQR/Canadian 2014 | 47872 | Support to the Office of the Quartet Representative
94838 | 94838 | DFATD 2015 Operational Support | 47872 | Support to the Office of the Quartet Representative
94974 | 94974 | IBRD Support to OQR | 47872 | Support to the Office of the Quartet Representative
97218 | 97218 | Office of Quartet Gas for Gaza | 47872 | Support to the Office of the Quartet Representative
105560 | 105560 | OQ Rule of Law | 47872 | Support to the Office of the Quartet Representative
105971 | 105971 | OQ Movement and Trade - Dutch | 47872 | Support to the Office of the Quartet Representative
58212 | 58212 | Rehab. of Maternity Wards | 48188 | Rehabilitation of Maternity Wards in Salfeet & Rafidia
58317 | 58317 | Justice Institutions: Planning | 48267 | Developing the capacities of the HJC
59147 | 59147 | West Bank Hospital Improvement | 48824 | EMRI - Emergency Medical Relief Initiative
59214 | 59214 | Widening Jericho Taybeh Road | 48868 | Jericho - Taybeh Road Rehabilitation
60507 | 60507 | Gender Equality& Women's Empow | 49552 | Gender Equality and Women's Empowerment in the oPt
60507 | 60507 | Gender Equality& Women's Empow | 49552 | Gender Equality and Women's Empowerment in the oPt
60507 | 60507 | Gender Equality& Women's Empow | 49552 | Gender Equality and Women's Empowerment in the oPt
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
61703 | 61703 | RAMALLAH COMMON PREMISES | 50096 | RAMALLAH COMMON PREMISES
75308 | 75308 | Environment RegulatoryFunction | 50122 | Public Administration and Institutional Development
75308 | 75308 | Environment RegulatoryFunction | 50122 | Public Administration and Institutional Development
61763 | 61763 | Early Recovery-Gaza (BCPR) | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
61765 | 61765 | Gaza Early Recovery | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
61765 | 61765 | Gaza Early Recovery | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
61765 | 61765 | Gaza Early Recovery | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
63805 | 63805 | Urgent Support-Agr. & Elec.IDB | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
63805 | 63805 | Urgent Support-Agr. & Elec.IDB | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
63805 | 63805 | Urgent Support-Agr. & Elec.IDB | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
69770 | 69770 | Cash Assistance -PMO | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
69770 | 69770 | Cash Assistance -PMO | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
69770 | 69770 | Cash Assistance -PMO | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
70673 | 70673 | Gaza Rubble Removal - CIDA | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71488 | 71488 | Rubble Removal - Gaza North | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71488 | 71488 | Rubble Removal - Gaza North | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71488 | 71488 | Rubble Removal - Gaza North | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71646 | 71646 | Rubble and Waste Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71646 | 71646 | Rubble and Waste Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71646 | 71646 | Rubble and Waste Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71646 | 71646 | Rubble and Waste Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
71646 | 71646 | Rubble and Waste Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
72955 | 72955 | UN Early Recovery Coordination | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
72955 | 72955 | UN Early Recovery Coordination | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
91916 | 91916 | Gaza Debris Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
91916 | 91916 | Gaza Debris Management | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92110 | 92110 | Bureij Camp School in Gaza | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92145 | 92145 | Emergency Cash Assistance Sida | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92145 | 92145 | Emergency Cash Assistance Sida | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92145 | 92145 | Emergency Cash Assistance Sida | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92457 | 92457 | Re-construction of houses | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92457 | 92457 | Re-construction of houses | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92457 | 92457 | Re-construction of houses | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
92895 | 92895 | North and south Rubble Removal | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
93992 | 93992 | Cash Assistance for Recons. | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
94619 | 94619 | Emergency Employment SW | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
96998 | 96998 | Crushing Concrete Rubble Italy | 50123 | Emergency Supply & Advanced Plan for Early Recovery-Gaza
63002 | 63002 | Strengthening SportsCapacities | 50848 | SPORTS PROGRAMME
63105 | 63105 | Peace Building in Waste Water | 50897 | Promote cross- boundary Wastewater management in oPt
88435 | 88435 | Waste Water Management | 50897 | Promote cross- boundary Wastewater management in oPt
63182 | 63182 | Support to the Community &NGOs | 50942 | Support Physical Disability Rehabilitation in Gaza
63303 | 63303 | Foreign Affairs Building | 51015 | Foreign Affairs Building
63303 | 63303 | Foreign Affairs Building | 51015 | Foreign Affairs Building
63303 | 63303 | Foreign Affairs Building | 51015 | Foreign Affairs Building
63535 | 63535 | Assist in food security improv | 51140 | Improve food security in marginalized area in Gaza Strip
77585 | 77585 | Providing beehives and other r | 51140 | Improve food security in marginalized area in Gaza Strip
63662 | 63662 | HIV/AIDS Response Program | 51220 | GFATM HIV/AIDS & Tuberculosis (TB)
63662 | 63662 | HIV/AIDS Response Program | 51220 | GFATM HIV/AIDS & Tuberculosis (TB)
63663 | 63663 | Tuberculosis Response Program | 51220 | GFATM HIV/AIDS & Tuberculosis (TB)
63663 | 63663 | Tuberculosis Response Program | 51220 | GFATM HIV/AIDS & Tuberculosis (TB)
69143 | 69143 | Co-ord support t achieve MDGs | 56482 | COORDINATED SUPPORT TO ACHIEVE THE MDGs
69508 | 69508 | Update of LG Diagnostic Report | 56673 | Local Governance Support Programme
69508 | 69508 | Update of LG Diagnostic Report | 56673 | Local Governance Support Programme
73971 | 73971 | ImprovedPropertyTax Collection | 56673 | Local Governance Support Programme
73971 | 73971 | ImprovedPropertyTax Collection | 56673 | Local Governance Support Programme
73971 | 73971 | ImprovedPropertyTax Collection | 56673 | Local Governance Support Programme
74700 | 74700 | Support to Local Economic Deve | 56673 | Local Governance Support Programme
69825 | 69825 | UNDP knowledge base | 56808 | BDP Programme of Support towards the Implementation of t
70416 | 70416 | Construction of 100 Housing Un | 57098 | Construction of 100 Housing Units
70416 | 70416 | Construction of 100 Housing Un | 57098 | Construction of 100 Housing Units
70540 | 70540 | Agro Industrial Road Improved | 57171 | Rehabilitation of the Agro Industrial Park Road
70906 | 70906 | Strengthening RoL Institutions | 57409 | Supporting the Rule of Law and Access to Justice
70906 | 70906 | Strengthening RoL Institutions | 57409 | Supporting the Rule of Law and Access to Justice
70906 | 70906 | Strengthening RoL Institutions | 57409 | Supporting the Rule of Law and Access to Justice
70906 | 70906 | Strengthening RoL Institutions | 57409 | Supporting the Rule of Law and Access to Justice
70906 | 70906 | Strengthening RoL Institutions | 57409 | Supporting the Rule of Law and Access to Justice
75076 | 75076 | Â Access to Justice: West Bank | 57409 | Supporting the Rule of Law and Access to Justice
75076 | 75076 | Â Access to Justice: West Bank | 57409 | Supporting the Rule of Law and Access to Justice
75076 | 75076 | Â Access to Justice: West Bank | 57409 | Supporting the Rule of Law and Access to Justice
75362 | 75362 | Â Gender and Juvenile Justice | 57409 | Supporting the Rule of Law and Access to Justice
75362 | 75362 | Â Gender and Juvenile Justice | 57409 | Supporting the Rule of Law and Access to Justice
75362 | 75362 | Â Gender and Juvenile Justice | 57409 | Supporting the Rule of Law and Access to Justice
75363 | 75363 | Â Access to Justice: Gaza Strip | 57409 | Supporting the Rule of Law and Access to Justice
75363 | 75363 | Â Access to Justice: Gaza Strip | 57409 | Supporting the Rule of Law and Access to Justice
75363 | 75363 | Â Access to Justice: Gaza Strip | 57409 | Supporting the Rule of Law and Access to Justice
75363 | 75363 | Â Access to Justice: Gaza Strip | 57409 | Supporting the Rule of Law and Access to Justice
75363 | 75363 | Â Access to Justice: Gaza Strip | 57409 | Supporting the Rule of Law and Access to Justice
75364 | 75364 | Â Building Confidence in RoL | 57409 | Supporting the Rule of Law and Access to Justice
75364 | 75364 | Â Building Confidence in RoL | 57409 | Supporting the Rule of Law and Access to Justice
77024 | 77024 | Hebron Courthouse Building | 57409 | Supporting the Rule of Law and Access to Justice
77024 | 77024 | Hebron Courthouse Building | 57409 | Supporting the Rule of Law and Access to Justice
77287 | 77287 | Initial Support:Justice Sector | 57409 | Supporting the Rule of Law and Access to Justice
80323 | 80323 | Anti-corruption&Accountability | 57409 | Supporting the Rule of Law and Access to Justice
80323 | 80323 | Anti-corruption&Accountability | 57409 | Supporting the Rule of Law and Access to Justice
80323 | 80323 | Anti-corruption&Accountability | 57409 | Supporting the Rule of Law and Access to Justice
70929 | 70929 | Mainstreaming Environment | 57418 | Mainstream Environment within oPt
70929 | 70929 | Mainstreaming Environment | 57418 | Mainstream Environment within oPt
70929 | 70929 | Mainstreaming Environment | 57418 | Mainstream Environment within oPt
72341 | 72341 | Excavating AgroIndustrialPark1 | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
78092 | 78092 | Jericho Park Water Extensions | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
81876 | 81876 | Jericho Park Admin. Building | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
85958 | 85958 | Jericho Park Electricity Works | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
87560 | 87560 | Capacity Developmnt Support P1 | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
89721 | 89721 | JerichoPark Industrial Support | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
93073 | 93073 | Jericho Park Telecommunication | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
94430 | 94430 | Capacity Development Support | 58277 | P1 - Construction of the Jericho Agro-Industrial Park
73758 | 73758 | Zohra Antiviolence Centers | 59090 | Italian Emergency Support Programme for Gaza & WB
73815 | 73815 | Upgrading Desalination Plant | 59090 | Italian Emergency Support Programme for Gaza & WB
73819 | 73819 | Solid Waste Management | 59090 | Italian Emergency Support Programme for Gaza & WB
73865 | 73865 | PAL-Construction of School in | 59143 | PAL-Construction of School in Gaza
74301 | 74301 | Improved Cultural Development | 59427 | MDG Culture & Development Programme in the oPt
74301 | 74301 | Improved Cultural Development | 59427 | MDG Culture & Development Programme in the oPt
75084 | 75084 | Palestinian Negotiations Suppo | 59876 | Peace Building in the oPt
75084 | 75084 | Palestinian Negotiations Suppo | 59876 | Peace Building in the oPt
93791 | 93791 | PALESTINIAN NEGOTIATIONS | 59876 | Peace Building in the oPt
93791 | 93791 | PALESTINIAN NEGOTIATIONS | 59876 | Peace Building in the oPt
75788 | 75788 | Improve the Capacity of CMWU | 60252 | Improve the Capacity of CMWU for Monitoring the Water
75793 | 75793 | Irrigation Systems and Water | 60256 | Irrigation Systems and Water Resources in the West Bank
72866 | 72866 | combat desertification in oPt | 60615 | Combat Desertification in oPt
83276 | 83276 | Inclusive and Participative Po | 60621 | Support to the Electoral Cycle
76676 | 76676 | Sharafat Housing project | 60779 | Sharafat Housing project
76892 | 76892 | Access Coordination and Monito | 60907 | Access Coordination and Monitoring Support
96819 | 96819 | Access Coordination Project | 60907 | Access Coordination and Monitoring Support
106652 | 106652 | Access Coordination & Monitori | 60907 | Access Coordination and Monitoring Support
77568 | 77568 | Economic Empowerment Jerusalem | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
77569 | 77569 | Land Development Jerusalem | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
77570 | 77570 | Support to CSOs in EJ | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
77570 | 77570 | Support to CSOs in EJ | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
77571 | 77571 | Jerusalem Homes Rehabilitation | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
79215 | 79215 | Small Enterprises Jerusalem | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
84404 | 84404 | Jerusalem Shops Rehabilitation | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
86299 | 86299 | Homes Rehabilitation Phase II | 61270 | JERUSALEM DEVELOPMENT - ISLAMIC DEVELOPMENT BANK
77583 | 77583 | Re-construction of totally dam | 61276 | Re-construction of totally damaged housing units in Gaza
78517 | 78517 | Export Development 1 | 61765 | EXPORT DEVELOPMENT IN THE WEST BANK PROJECT â€“ CANADIAN I
79764 | 79764 | Engineering Services â€“ UN Prog | 62322 | Engineering Services â€“ UN Programmes/Agencies
79915 | 79915 | Ren. and Rehab. of Maternities | 62322 | Engineering Services â€“ UN Programmes/Agencies
79915 | 79915 | Ren. and Rehab. of Maternities | 62322 | Engineering Services â€“ UN Programmes/Agencies
79915 | 79915 | Ren. and Rehab. of Maternities | 62322 | Engineering Services â€“ UN Programmes/Agencies
80747 | 80747 | Interpeace Israel - Base for D | 63882 | Interpeace Israel - Base for Development
80747 | 80747 | Interpeace Israel - Base for D | 63882 | Interpeace Israel - Base for Development
80747 | 80747 | Interpeace Israel - Base for D | 63882 | Interpeace Israel - Base for Development
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
80763 | 80763 | Supporting Statehood-Palestine | 63909 | Supporting Governance for Palestinian statehood
104084 | 104084 | Strengthening Pal Public Insti | 63909 | Supporting Governance for Palestinian statehood
81280 | 81280 | DEVELOPMENT EFFECTIVENESS DE | 64505 | DEVELOPMENT EFFECTIVENESS DE
81280 | 81280 | DEVELOPMENT EFFECTIVENESS DE | 64505 | DEVELOPMENT EFFECTIVENESS DE
81280 | 81280 | DEVELOPMENT EFFECTIVENESS DE | 64505 | DEVELOPMENT EFFECTIVENESS DE
81280 | 81280 | DEVELOPMENT EFFECTIVENESS DE | 64505 | DEVELOPMENT EFFECTIVENESS DE
82361 | 82361 | Mainstreaming Climate Change | 66131 | Low carbon development and climate change resilient Prog
82361 | 82361 | Mainstreaming Climate Change | 66131 | Low carbon development and climate change resilient Prog
82361 | 82361 | Mainstreaming Climate Change | 66131 | Low carbon development and climate change resilient Prog
86815 | 86815 | Hydro Climate Modeling | 66131 | Low carbon development and climate change resilient Prog
86815 | 86815 | Hydro Climate Modeling | 66131 | Low carbon development and climate change resilient Prog
94505 | 94505 | Reconstruction works for Atta | 66569 | Rehabilitation and Reconstruction of health premises
83499 | 83499 | Infrastructure Development | 68110 | Alternative Infrastructure Development in the oPt
83499 | 83499 | Infrastructure Development | 68110 | Alternative Infrastructure Development in the oPt
84013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM
84013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM
84013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM
84013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM
84013 | 84013 | Community Resilience Program | 69435 | Communitry Resilience & Dev. Prog. for Area C & EJRM
85915 | 85915 | FUMT_PD | 71773 | Field_Unit_Monitoring_Travel_Budget_FUMT
86777 | 86777 | Cultural Heritage Safeguarding | 74323 | Safeguarding of Cultural Heritage in the Old City
87068 | 87068 | Medical Procurement for Gaza | 74904 | Procurement of Drugs to Gaza
87457 | 87457 | Establish Jerusalem Library | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
87760 | 87760 | Right to Education | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
88256 | 88256 | FAIR-Development of Al Hurriya | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
90063 | 90063 | Makassed Neurology Department | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
90064 | 90064 | InfrastructureUpgradeSt.Joseph | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
90065 | 90065 | Homes Rehabilitation Phase III | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
90824 | 90824 | Resilience&Access Facilitation | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
90824 | 90824 | Resilience&Access Facilitation | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
97586 | 97586 | Access to Cancer Care in Jerus | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
106598 | 106598 | Support to Edu Sector in EJ | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
106598 | 106598 | Support to Edu Sector in EJ | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
106598 | 106598 | Support to Edu Sector in EJ | 75685 | FAIR-Facilitating Access to Infrastructure Resilience
88270 | 88270 | Capacity of Justice & Security | 77565 | Strengthen ROL 2nd phase in OPT
98489 | 98489 | Support Legal aid in Palestine | 77565 | Strengthen ROL 2nd phase in OPT
105165 | 105165 | Sawasya II Inception Phase | 77565 | Strengthen ROL 2nd phase in OPT
88464 | 88464 | Disaster Risk Reduction | 77909 | Resilience Against Natural Disasters â€œRANDâ€
88901 | 88901 | Rapid Support - Infrastructure | 78805 | â€œHIGH IMPACT MICRO-INFRASTRUCTURE INITIATIVE (HIMII)â€
89687 | 89687 | Rehabilitation of Water - Area | 78805 | â€œHIGH IMPACT MICRO-INFRASTRUCTURE INITIATIVE (HIMII)â€
88974 | 88974 | Development Cultural Tourism | 78870 | Support to Development of Cultural Tourism
89658 | 89658 | Advocacy &knowledge production | 79772 | Knowledge Management for Advocacy
92109 | 92109 | National and Social Cohesion | 83801 | Palestinian National Unity and Social Cohesion Programme
92109 | 92109 | National and Social Cohesion | 83801 | Palestinian National Unity and Social Cohesion Programme
92109 | 92109 | National and Social Cohesion | 83801 | Palestinian National Unity and Social Cohesion Programme
94529 | 94529 | Support Employment Generation | 87577 | Support to Employment Generation
104547 | 104547 | Ph II Levelling & Well | 87577 | Support to Employment Generation
104548 | 104548 | JAIP Solid Waste Mangmt System | 87577 | Support to Employment Generation
94044 | 94044 | Productivity&Urban Renewal JRS | 87585 | Productivity and Urban Renewal in East Jerusalem
94044 | 94044 | Productivity&Urban Renewal JRS | 87585 | Productivity and Urban Renewal in East Jerusalem
94630 | 94630 | Expansion of Jericho landfill | 87707 | solid waste managment WB
94739 | 94739 | Right to Education in Gaza | 87840 | Right to Education in the Gaza Strip
96413 | 96413 | Periodic Maintenance of School | 87840 | Right to Education in the Gaza Strip
96619 | 96619 | Renewable energy for All â€“Gaza | 91323 | Renewable energy for All â€“ Gaza Strip
98334 | 98334 | Improved Water and Waste Water | 94074 | Improved Water and Waste Water in Gaza Strip
98764 | 98764 | Energy networks recovered | 94677 | Rehabilitation of Electricity Power Distribution Network
100915 | 100915 | LAND RECLAMATION & CB MOA | 96078 | LAND & AGRICULTURE & IRRIGATION
100082 | 100082 | JAIP/BUSINESS DEV CONSULT-SERV | 96081 | BUSINESS DEVELOPMENT CONSULTING SERVICES
102665 | 102665 | Support to Al Quds University | 99388 | Support to Jerusalem based institutions
102677 | 102677 | Early recovery for Economy | 99398 | Rehabilitation & Construction of Gaza Industrial Estate
102744 | 102744 | Empowering Youth | 99465 | Emergency Response to Palestinian Youth Despair
102747 | 102747 | OFID House Rehabilitation II | 99470 | House Rehabilitation II
103834 | 103834 | Supprt New Schools E Jerusalem | 99487 | Provision of social services in West Bank and Jerusalem
103834 | 103834 | Supprt New Schools E Jerusalem | 99487 | Provision of social services in West Bank and Jerusalem
103835 | 103835 | Support to Health Sector in WB | 99487 | Provision of social services in West Bank and Jerusalem
104005 | 104005 | Support Housing in E.Jerusalem | 99487 | Provision of social services in West Bank and Jerusalem
108030 | 108030 | Wadi Gaza coastal wetland | 107971 | Protection of natural reserves and coastal wetlands
108030 | 108030 | Wadi Gaza coastal wetland | 107971 | Protection of natural reserves and coastal wetlands